**FY 2021 – FY 2025 Consolidated Plan & FY 2021 Budget Timeline**

|  |  |  |
| --- | --- | --- |
| Spring/Summer 2019 |  | Data gathering, GIS/map gathering  Consultant study on housing needs |
| Spring/Summer 2019 |  | Focus Groups & Stakeholder Outreach (see attached) |
| September 1, 2019 |  | Notice of Consolidated Plan Process &  Budget Process is emailed/posted/printed |
| October 24, 2019 |  | 1st Public Hearing on Consolidated Plan/FY 2021 Budget Process at ACDS  6:30 p.m. – 8:30 p.m.  *Goal:* Kick off Consolidated Plan process, solicit input on needs in community, kick off budget process |
| November 1, 2019 |  | FY 2021 Budget Applications due to ACDS |
| December 5, 2019 |  | 2nd Public Hearing on Consolidated Plan  4:30 p.m. – 6:00 p.m.  *Goal: Work with public to articulate goals and strategies for Con Plan and prioritize those goals* |
| January 23, 2020 |  | 3rd Public Hearing on Consolidated Plan & FY 2021 Budget Process  6:30 p.m. – 8:30 p.m.  *Goal: Solicit feedback from public on final Con Plan goals and strategies, present and solicit feedback on FY 2021 Budget priorities* |
| Early March 2020 |  | Draft Consolidated Plan – published  Public comment period - 30 days |
| Early April County Council Meeting |  | Introduced to County Council  Public comment period – 30 days |
| June 15, 2020 |  | Submit Final FY 2021 – FY 2025 Consolidate Plan/FY 2021 Budget to HUD |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

All public meetings will be held at the offices of Arundel Community Development Services, Inc. at 2666 Riva Road, Suite 210, Annapolis, MD 21401. ACDS is ADA accessible. If you wish to attend and require a **special accommodation** (e.g. interpreter for deaf and hard of hearing or an interpreter for persons with limited English proficiency) please contact [kashby@acdsinc.org](mailto:kashby@acdsinc.org) or 410-222-7805 no later than **7 business days prior** to the public meeting.

K:\Planning Documents\Consolidated Plan Development\2021-2025 Consolidated Plan\Timelines\PublicTimeline\_Con Plan and 2021 Budget.Board.2019.docx